## Summary
dev.effortsengineers.in – Review Checklist Summary
Review date: 30 Oct 2026. Based on text content of Home, Products, Services, About, Contact and Warranty pages (visuals and interactive features not tested).
Priority | Total | Open | In progress | Done
High | 9 | 9 | 0 | 0
Medium | 16 | 16 | 0 | 0
Low | 5 | 5 | 0 | 0
Total | 30 | 30 | 0 | 0
Sheets: Checklist (set Owner/Status per item) · Facts to Confirm (decide one correct value for each repeated detail).

## Checklist
ID | Category | Page(s) | Issue found | Recommended fix | Priority | Owner | Status | Notes
EE-01 | Content consistency | Footer, Contact, Products, Services | Two different WhatsApp numbers: +91 90960 01010 (footer, Contact hotline) and +91 90960 26622 (Products/Services/Contact CTAs). | Choose one primary WhatsApp number; label the other (e.g. 'Breakdown hotline') or drop it. Store in one config value so every page uses it. | High |  | Open
EE-02 | Content consistency | Top bar, Footer, Contact | Three different emails: efforts.engineers@HOTMAIL.COM, milan@effortsengineers.in, saurabh@effortsengineers.in. The top bar shows different emails on different pages. | Use domain emails only (e.g. sales@ / info@) in one config value. Avoid the all-caps Hotmail address on a business site. | High |  | Open
EE-03 | Content consistency | Footer vs Contact | Address mismatch: footer says Shop 10/11, Shirole Park, Shivajinagar (411016); Contact page says Erandwane (411004) and a plant at Plot 48, MIDC Bhosari (411026). | Confirm the real corporate office and workshop addresses and use the same text everywhere, including Google Maps and schema. | High |  | Open
EE-04 | Content consistency | Home, Global Reach, About | Export reach quoted as '15+', '45+' and '15–20' countries. | Pick one verified number and use it in the top bar, stats, hero badge, logistics text and timeline. | High |  | Open
EE-05 | Content consistency | Home, About | Years in business stated as 'since 1986', '40+ years', 'over three decades' and '30+ years'. | Use 'Since 1986' / '40 years' consistently; update the footer boilerplate. | Medium |  | Open
EE-06 | Content consistency | About | Timeline heading says '1994 to 2026' but the first milestone is 1986. | Change the heading to '1986 to 2026'. | Medium |  | Open
EE-07 | Content consistency | All (footer) | Footer 'Compatible Brands' lists 8 brands on some pages and 16 on others. | Use one shared footer component with the same brand list on every page. | Low |  | Open
EE-08 | Content consistency | Home, Contact | Response-time promise differs: '2 hours' (home) vs '2-4 hours' (Contact). | Use one promise the sales team can actually meet. | Medium |  | Open
EE-09 | Wording | Home | Typo in testimonial: 'Refrigerigeration'. | Correct to 'Refrigeration'. | Low |  | Open
EE-10 | Wording | All (footer, Warranty) | Awkward phrase 'Associated with Manufacturers with ISO 9001 Certification Certified'. | Reword, e.g. 'ISO 9001-certified manufacturing partners', and make sure it matches the certificate scope. | Medium |  | Open
EE-11 | Wording | About | '20 full filter containers' looks like a typo. | Confirm intended wording (e.g. 'full container loads'). | Low |  | Open
EE-12 | Claims | Home, Warranty | 'Direct-from-manufacturer' and 'in-house CNC manufacturing' sit alongside 'associated manufacturers'. Also 'zero defect', '100% replacement', 'up to 40% savings' and 'guaranteed' delivery to Europe/Africa. | Align wording with what is actually made in-house; add warranty terms and conditions; soften delivery guarantees where customs can delay. | Medium |  | Open
EE-13 | SEO | All pages | Same <title> and meta description on every page checked. | Write unique title and description for each page (e.g. 'Kirloskar KC Compressor Spares ¦ Efforts Engineers'). | High |  | Open
EE-14 | SEO | Products | Catalog is JavaScript-rendered ('Loading catalog…'); crawlers may see nothing. | Server-side render the catalog; give each category/part its own URL; check with 'View source' and Search Console URL inspection. | High |  | Open
EE-15 | SEO | Site-wide | No evidence of sitemap, structured data or per-page canonical tags. | Add sitemap.xml, robots.txt, canonical tags, Organization/LocalBusiness, Product and FAQ schema. | Medium |  | Open
EE-16 | SEO | Warranty | FAQ answers are collapsed and were not visible in the page text. | Make sure answer text is in the HTML (collapsed with CSS, not loaded on click only). | Medium |  | Open
EE-17 | SEO | Cutover | dev.effortsengineers.in uses absolute URLs and must not be indexed. | Set noindex on dev; make base URL/canonical configurable; re-check all absolute links at cutover. | High |  | Open
EE-18 | Content gaps | Home, Product Sourcing | Copeland, Ingersoll Rand, Atlas Copco and CPT have only a 'share your model' placeholder; Accel Sabroe duplicates Sabroe. | Add real model ranges or merge into one 'Other makes' block; merge Accel Sabroe into Sabroe. | Medium |  | Open
EE-19 | Content gaps | Home | Testimonials show name and role only. | Add company name, and photo/logo with permission. | Low |  | Open
EE-20 | Content gaps | Home | Certificates are only linked from Global Reach. | Show certificate/ISO thumbnails or a logo strip on the home page. | Medium |  | Open
EE-21 | Content gaps | Home | No short 'How it works' flow. | Add 3 steps: send part ref, quote in 2 hours, dispatch. | Low |  | Open
EE-22 | Look & feel | All | Visual design, spacing and imagery could not be assessed (text-only review). | Do a visual pass: hero imagery, page-specific photos, spacing, colour contrast, consistent buttons. | Medium |  | Open
EE-23 | Functionality | Home, Contact, Warranty | RFQ and RMA forms not tested. | Submit test entries: check confirmation message, email delivery to the right inbox, validation, and spam protection (honeypot/CAPTCHA). | High |  | Open
EE-24 | Functionality | Header | Quote Builder not tested. | Test with a real multi-line part list; check PDF/quotation download and the email received. | Medium |  | Open
EE-25 | Functionality | Header, Footer | Portal Login and /client/dashboard (Order Tracking) not tested. | Test register/login/logout; check what a logged-out visitor sees on /client/dashboard. | Medium |  | Open
EE-26 | Functionality | Warranty | Serial / invoice warranty status check not tested. | Test with valid, invalid and empty input; check error messages. | Medium |  | Open
EE-27 | Functionality | Services, Contact | Pages mention the AI chatbot on the bottom right. | Confirm the chatbot loads on every page and answers sensibly; add a fallback to WhatsApp. | Medium |  | Open
EE-28 | Functionality | Home, Global Reach | /brochure.pdf and certificate downloads are linked. | Click each download; confirm files exist, are current and have sensible sizes. | Medium |  | Open
EE-29 | Functionality | All | Mobile layout not verified. | Test on real phones and tablets: menu, long brand dropdown in forms, tap targets, sticky WhatsApp button. | High |  | Open
EE-30 | Functionality | All | Page speed and accessibility not measured. | Run Lighthouse (mobile); fix image sizes, contrast, keyboard focus on dropdown menus, form labels and alt text. | Medium |  | Open

## Facts to Confirm
Item | Values found on dev site (where) | Confirmed value (fill in) | Notes
Primary WhatsApp number | +91 90960 01010 (footer, Contact hotline); +91 90960 26622 (Products/Services/Contact CTAs)
Breakdown hotline | +91 90960 01010 (Contact page)
Landline(s) | +91 20 2567 8102 (top bar, footer); +91-20-25678102 / +91-20-25678972 (Contact)
General / sales email | efforts.engineers@HOTMAIL.COM (most pages); milan@effortsengineers.in (Products page)
Contact person email | saurabh@effortsengineers.in (Contact)
Contact person | Mr. Saurabh S Salvi (Contact); Mr. Saurabh Salvi (testimonial)
Corporate office address | Shop No. 10, Shirole Park, Senapati Bapat Rd, Shivajinagar, Pune 411016 (footer) vs Erandwane, Pune 411004 (Contact)
Workshop / plant address | Shop No. 11, Shirole Park, Shivajinagar, Pune 411016 (footer) vs Plot 48, MIDC Bhosari, Pune 411026 (Contact)
Year established | 1986 (home, timeline); '40+ years', 'over three decades', '30+ years' elsewhere
Export countries | 15+ (home top bar, one stats strip); 45+ (home stats, other top bars); 15–20 (About timeline)
Quote response time | Within 2 hours (home); 2–4 hours (Contact)
Operating hours | Mon–Sat 8:30 AM – 7:30 PM IST; 24/7 breakdown dispatch for contracted plants (Contact)
Delivery timeline claims | 24–48h India metros; 2–3 days Gulf (air); 3–5 days Europe/Africa/SE Asia (air) (home)
Manufacturing statement | 'Direct-from-manufacturer', 'in-house CNC' vs 'Associated with manufacturers' (home, Warranty)
ISO 9001 wording | 'Associated with Manufacturers with ISO 9001 Certification Certified' (footer, Warranty)
Savings claim | 'Up to 40% cost savings' (home)
Legend: yellow cells are for you to fill. Once confirmed, use these values in one shared config/footer so every page matches.